## Asset Inventory
ACME FINANCIAL SERVICES ASSET INVENTORY
Enterprise Risk Assessment & Risk Register
Asset ID | Asset Name | Asset Type | Business Owner | Technical Owner | Data Classification | Criticality | Recovery Priority | Business Purpose | Location / Platform | Related Risks | Notes
A-001 | Customer Database | Database | Operations | IT/Security | Restricted | Critical | Tier 1 | Stores customer account and financial information | Internal Database Environment | Unauthorized Access, Data Leakage | Contains customer PII and financial records
A-002 | Microsoft 365 | SaaS | Business Operations | IT | Confidential | High | Tier 2 | Provides email, collaboration, and document storage | Microsoft 365 Cloud | Phishing, Credential Theft | MFA enabled
A-003 | AWS Cloud Environemnt | Cloud Infrastructure | IT Leadership | Cloud Team | Restricted | Critical | Tier 1 | Hosts cloud applications and supporting infrastructure | AWS | Cloud Misconfiguration Data Exposure | Production workloads hosted in AWS
A-004 | Salesforce CRM | SaaS | Sales Operations | IT Applications | Confidential | High | Tier 2 | Manages customer relationships and sales activity | Salesforce Cloud | Unauthorized Access, Third-Party Risk | Integrated with Microsoft 365
A-005 | Employee Laptops | Endpoint | Department Mangers | IT Support | Internal Use | Medium | Tier 3 | Provides employee access to business systems | Company Managed Devices | Malware, Device Theft | Full disk encryption required
A-006 | VPN Infrastructure | Network Infrastructure | IT Leadership | Network Team | Confidential | High | Tier 2 | Provides secure remote access to internal systems | Corporate VPN | Credential Theft, Unauthorized Access | MFA required
A-007 | Third-Party Vendors | External Service Provider | Vendor Management | GRC Team | Restricted | High | Tier 2 | Supports payroll, cloud, compliance, and business services | Third-Party Platforms | Vendor Breach, Supply Chain Attack | Subject to annual vendor reviews

## Risk Register
ACME FINANCIAL SERVICES ASSET INVENTORY
Enterprise Risk Assessment & Risk Register
Risk ID | Asset | Threat | Vulnerability | Existing Controls | Likelihood | Impact | Inherent Risk Score | Risk Rating | Treatment Strategy | Risk Owner | Status | Review Date | Residual Risk | Comments
R-001 | Microsoft 365 | Phishing | User susceptability to phishing emails | Security Awareness Training, MFA | 4 | 5 | 20 | Critical | Mitigate | IT Security Team | Open | 06/30/2026 | Moderate | Additional Phishing Simulations Planned
R-002 | Customer Database | Unauthorized Access | Excessive Permissions | Access Management Policy, MFA | 3 | 5 | 15 | High | Mitigate | IT Security Team | Open | 07/15/2026 | Moderate | Quarterly access reviews implemented
R-003 | AWS Cloud Environment | Cloud Misconfiguration | Improper Security Settings | Cloud Service Provider Policy | 4 | 5 | 20 | Critical | Mitigate | Cloud Team | Open | 08/14/2026 | Moderate | Continuous Configuration Monitoring Implemented
R-004 | Employee Laptops | Device Theft | Mobile Workforce | Full Disk Encryption, MDM | 3 | 4 | 12 | High | Mitigate | IT Support Team | In Progress | 08/22/2026 | Low | Confirm encryption coverage for all endpoints
R-005 | Third-Party Vendors | Vendor Breach | Insufficient Vendor Oversight | Third-Party Management Policy | 3 | 5 | 15 | High | Transfer | GRC Team | Open | 09/15/2026 | Moderate | Annual Vendor Security Reviews required
R-006 | VPN Infrastructure | Credential Theft | Password Reuse | MFA, VPN Monitoring | 4 | 4 | 16 | Critical | Mitigate | Network Infrastructure Team | Open | 09/28/2026 | Moderate | Strengthen conditional access rules
R-007 | Salesforce CRM | Third-Party Integration Compromise | API Dependencies | Vendor Security Reviews, Access Controls | 3 | 4 | 12 | High | Mitigate | Application Support Team | In Progress | 10/15/2026 | Moderate | Review Third-Party app integrations

## Risk Matrix
Risk Rating Criteria
Likelihood Score | Rating | Description | Impact Score | Rating | Description
1 | Rare | Unlikely to occur | 1 | Low | Minimal impact
2 | Unlikely | Could occur occasionally | 2 | Minor | Limited operational impact
3 | Possible | May occur under certain conditions | 3 | Moderate | Noticeable business disruption
4 | Likely | Expected to occur | 4 | Major | Significant operational or regulatory impact
5 | Almost Certain | Expected to occur frequently | 5 | Severe | Critical business, financial, or reputational impact
Risk Score | Rating
1-5 | Low
6-10 | Medium
11-15 | High
16-25 | Critical

## Risk Heat Map
Risk Heat Map
Likelihood ↓ / Impact → | 1 | 2 | 3 | 4 | 5
5 Almost Certain | Medium | High | Critical | Critical | Critical
4 Likely | Medium | Medium | High | Critical | Critical
3 Possible | Low | Medium | Medium | High | Critical
2 Unlikely | Low | Low | Medium | Medium | High
1 Rare | Low | Low | Low | Medium | Medium

## Lists
Threats | Treatment Strategy | Risk Owner | Status | Likelihood | Impact | Risk Rating | Residual Risk Score
Phishing | Mitigate | IT Security | Open | 1 | 1 | Low | Low
Malware | Transfer | Applications Support Team | In Progress | 2 | 2 | Medium | Moderate
Ransomware | Accept | Cloud Team | Mitigated | 3 | 3 | High | High
Credential Theft | Avoid | IT Support | Accepted | 4 | 4 | Critical | Critical
Unauthorized Access |  | GRC Team | Closed | 5 | 5
Insider Threat |  | Network Infrastructure Team
Data Leakage |  | Business Operations
Cloud Misconfiguration |  | Vendor Management
Vendor Breach
Supply Chain Attack
Denial of Service
System Failure
Patch Management Failure
Natural Disaster
Regulatory Noncompliance
AI Model Misuse
Device Theft
Third Party Integration Compromise
Compromise

## Definitions
Definitions
Term | Definition
Asset | A system, application, data store, device, vendor, or platform that supports business operations.
Threat | A potential event or actor that could exploit a weakness and cause harm.
Vulnerability | A weakness or gap that could be exploited by a threat.
Existing Controls | Current safeguards that reduce likelihood or impact.
Likelihood | Probability that a risk scenario could occur.
Impact | Business harm if the risk scenario occurs.
Inherent Risk | Risk level before additional treatment or mitigation.
Residual Risk | Remaining risk after existing controls or planned treatment actions.
Treatment Strategy | Management decision to mitigate, transfer, accept, or avoid risk.
Risk Owner | Person or team accountable for managing the risk.
Status | Current state of risk treatment activities.